## 1-Instructions
Prepare Agenda: Review the 2-Agenda Assembly worksheet and add the project details in the orange cells. The cells with a drop down option are also shown in orange and with a pattern. You may also want to consider completing the additional fields highlighted in the Emergency Notification and Project Personnel worksheets. To help the meeting flow, note that the Submittals and contacts are included in the agenda under the related category. This information is automatically populated into the other worksheets and those worksheets may be printed separately.
Printing: For printing the 2-Agenda Assembly worksheet column A includes a dropdown with YES/NO to allow hiding rows that do not apply. Go through the rows and select YES if the row applies to the project and NO if it does not. Some rows only allow YES because that information applies to all projects. The NO option is shown in red to help identify which rows to hide. When you are ready to print, first filter the NO rows by selecting the triangle in the first cell A1, "Include?" and deselect NO. You may consider adjusting the page breaks for printing. After doing this, only the visible rows will be shown when printing. Note that the "Include?" information from the Agenda is copied to the column A in the Submittal List and Project Personnel worksheets and all you need to do is filter the NOs.
Note there are additional comment fields (FIO) and formatting notes to the right of the form. For example, the phone number fields only need numbers and you do not need to use () or -. The date fields are formatted to: MM/DD/YYYY and the time fields are formatted to: HH:MM AM/PM.
Version 2022_01

## 2-Agenda Assembly Landscape
Include? | 0 |  | 0
ALL | Name |  | Title |  | Organization |  | Phone Number | E-Mail Address
ALL | [10 empty] | Phone Number - numbers only symbols not needed.
ALL
ALL
ALL
ALL
ALL
ALL
ALL | [10 empty] | Phone Number - numbers only symbols not needed.
ALL
ALL
ALL
ALL
ALL
ALL
ALL
ALL
ALL
NO | Name |  | Title |  | Organization |  | Phone Number | E-Mail Address |  |  | Phone Number - numbers only symbols not needed.
NO
NO
NO
NO
NO
NO
NO | [10 empty] | Phone Number - numbers only symbols not needed.
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO | Name |  | Title |  | Organization |  | Phone Number | E-Mail Address |  |  | Phone Number - numbers only symbols not needed.
NO
NO
NO
NO
NO
NO
NO
NO
NO | [10 empty] | Phone Number - numbers only symbols not needed.
NO
NO
NO
NO
NO
NO
NO
NO
ALL | I. Project Information | [8 empty] | I. Project Information - Additional Comments
ALL | Project Code: |  |  |  |  | Project Number:
ALL
ALL | Description:
ALL
ALL | Location (route, begin milepost, and end milepost):
ALL
ALL | Estimated Construction
ALL |  | Start Date: |  |  |  | End Date: |  |  |  |  | Date format MM/DD/YYYY
ALL
ALL | II. Introductory Statement | [8 empty] | II. Introductory Statement - Additional Comments
ALL | We would like to start by stating that the Colorado State Department of Transportation (CDOT) welcomes you to the Project Team. Please join us in meeting our goals to make this a successful and high quality project. We will not just meet the schedule but drive it. We will provide the most value for every dollar in order to be a part in providing the best transportation system in Colorado. Here at CDOT we work and live safely! We take a can-do attitude, working together to identify and solve problems. We are committed to quality. We hold ourselves to the highest moral and ethical standards. There is an expectation of excellence, integrity, respect, and success from each team member.
NO | Add Project Charter (Optional)
NO
ALL | EMERGENCY PHONE NUMBERS
ALL | Physician |  |  |  |  | or |  |  |  |  | Phone Number - numbers only symbols not needed.
ALL | Hospital |  |  |  |  | or
ALL | Ambulance |  |  |  |  | or
ALL | Fire |  |  |  |  | or
ALL | Police |  |  |  |  | or
ALL
ALL | CDOT Form No. 140 [1/93]
ALL
ALL | III. Key Personnel | [8 empty] | III. Key Personnel - Additional Comments
ALL | CDOT Personnel
ALL | Project Engineer
ALL | Name: |  |  |  |  | Office #: |  |  |  |  | Phone Number - numbers only symbols not needed.
ALL | Email: |  |  |  |  | Cell #:
NO | Assistant Project Engineer
NO | Name: |  |  |  |  | Office #:
NO | Email: |  |  |  |  | Cell #:
YES | Inspector 1
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
NO | Inspector 2
NO | Name: |  |  |  |  | Office #:
NO | Email: |  |  |  |  | Cell #:
NO | Inspector 3
NO | Name: |  |  |  |  | Office #:
NO | Email: |  |  |  |  | Cell #:
ALL | Resident Engineer
ALL | Name: |  |  |  |  | Office #:
ALL | Email: |  |  |  |  | Cell #:
ALL | Maintenance Representative
ALL | Name: |  |  |  |  | Office #:
ALL | Email: |  |  |  |  | Cell #:
ALL | Contractor Personnel
ALL | (Contractor Company Name Here)
ALL | Address: |  |  |  |  | Phone: |  |  |  |  | Phone Number - numbers only symbols not needed.
YES | Project Manager
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | Individual is authorized to sign Change Orders?
ALL | Superintendent
ALL | Name: |  |  |  |  | Office #:
ALL | Email: |  |  |  |  | Cell #:
ALL | Individual is authorized to sign Change Orders?
NO | Alternate Superintendent 1
NO | Name: |  |  |  |  | Office #:
NO | Email: |  |  |  |  | Cell #:
NO | Individual is authorized to sign Change Orders?
NO | Alternate Superintendent 2
NO | Name: |  |  |  |  | Office #:
NO | Email: |  |  |  |  | Cell #:
NO | Individual is authorized to sign Change Orders?
NO | Other
NO | Name: |  |  |  |  | Office #: |  |  |  |  | Phone Number - numbers only symbols not needed.
NO | Email: |  |  |  |  | Cell #:
NO | Individual is authorized to sign Change Orders?
NO | Local Agency Representatives
NO | (Local Agency Name Here)
NO | Name: |  |  |  |  | Office #: |  |  |  |  | Phone Number - numbers only symbols not needed.
NO | Email: |  |  |  |  | Cell #:
NO | (Local Agency Name Here)
NO | Name: |  |  |  |  | Office #:
NO | Email: |  |  |  |  | Cell #:
NO | (Local Agency Name Here)
NO | Name: |  |  |  |  | Office #:
NO | Email: |  |  |  |  | Cell #:
ALL | IV. Project Administration | [8 empty] | IV. Project Administration - Additional Comments
ALL | A. Authority of the Engineer | [8 empty] | A. Authority of the Engineer - Additional Comments
ALL | The Contractor is reminded of the authority and duties of the Project Engineer outlined in subsections 105.01 and 105.14 of the Standard Specifications. The Project Engineer will decide all questions regarding the quality and acceptability of the work. The Contractor is cautioned that only the Project Engineer is authorized to provide information, clarification, or interpretation regarding plans, specifications, and any other contract documents or requirements, per subsection 105.09 of the Standard Specifications. In the case where the Engineer is a Consultant Project Engineer these decisions will be made by the Resident Engineer. Solicitation and receipt of information by the Contractor from any other CDOT representative will not be considered valid for administration of the project. All submittals required by the Contract shall be submitted to the Project Engineer. Submittals made to and received by other CDOT representatives will not be considered valid for the purpose of administration of the Contract.
YES | Submittal | [5 empty] | Specification | Due | Received
YES | IV A1 | Form 1378 - Contractor Selection of Litigation or Arbitration |  |  |  |  | 105.24 (f) | Pre-Con
YES | IV A2 | Form 1379 - Dispute Review Board Three Party Agreement for Standing Board |  |  |  |  | 105.23 (b) | by 15 days of Contract Execution
ALL | B. Payment | [8 empty] | B. Payment - Additional Comments
ALL | 1. Estimate cutoff date: |  |  | e.g., 25th of each month
ALL | 2. Electronic Funds Transfer forms are available from the Accounts Payable Office at dot_accounts_payable@state.co.us.
ALL | 3. Prompt Payment: Per Subsection 107.01 and 109.06 the Contractor to comply with the Prompt Payment Law (C.R.S. 24-91-103) and shall submit monthly payment confirmation through B2GNow. Failure to submit required information may result in CDOT withholding of payments.
ALL | 4. Does the Contractor intend to provide securities in lieu of cash retainage to be withheld from payments?
ALL | 5. The Engineer will not reduce retainage until all project work is complete, the project has been accepted, and all documentation is received and accepted. When the Contractor requests an exception, consent of the Surety is required when releasing retainage before final payment.
ALL | 6. The Contractor shall complete and submit all required forms, instruct subcontractors on the proper procedures for completing forms, and ensure that all forms and reports are submitted and approved in a timely basis. Failure to do so may result in delays in payment.
ALL | 7. The initial payment schedule is required within 15 days of Award of the Contract. CDOT will not execute the contract without an initial payment schedule. An update is required on the first day of each month during construction. Failure to provide an update will result in a delay of the next progress payment.
ALL | Submittal | [5 empty] | Specification | Due | Received
ALL | IV B1 | Initial Payment Schedule [2 by 15 days of Award] |  |  |  |  | 108.04(a) | 2
ALL | IV B2 | Payment Schedule Updates |  |  |  |  | 108.04(b) | 1st of Month
ALL | IV B3 | Payment/Drawdown Schedule Update |  |  |  |  | 108.04(b) | 1st of Month
ALL | C. Contract Time | [8 empty] | C. Contract Time - Additional Comments
ALL | 1. Notice to Proceed Date: |  |  |  |  | Anticipated Start Date: |  |  |  |  | Date format MM/DD/YYYY
ALL | 2. Contract Time Type is: | [7 empty] | days or date |  | No Date format for this field
ALL | 3. Date project time charges begin:
ALL | 4. Working time restrictions noted in the plans are:
ALL | 5. The Contractor will work: |  |  |  | days/ week |  |  | shifts/ day
ALL | 6. The Contractor's working hours are: | [5 empty] | to
ALL | 7. Special concerns:
ALL | D. Project Schedule | [8 empty] | D. Project Schedule - Additional Comments
ALL | 1. The Contractor's approved CPM Baseline schedule or CPM Preliminary schedule is required to begin work.
ALL | 2. The Schedule update is required by the estimate cutoff date: and before payment.
ALL | Submittal | [5 empty] | Specification | Due | Received
ALL | IV D1 | Baseline Schedule or Preliminary Schedule [3 by 14 days after award and approved before work starts] |  |  |  |  | 108.03 | 3
ALL | IV D2 | Scheduling Software Selection - Microsoft Project or Oracle Primavera [4 by 14 days after award] |  |  |  |  | 108.03(b) | 4
ALL | IV D3 | When Preliminary Schedule submitted full Baseline Schedule [5 by 45 days after award and approved before continuing past first 60 days] |  |  |  |  | 108.03(c) 108.03(e) | 5
ALL | IV D4 | Project Schedule Update including time-scaled logic diagram, native software file (*.xer or *.mpp), and reports [6 by estimate cutoff date] |  |  |  |  | 108.03(c) 108.03(f) | 6
ALL | IV D5 | Weekly Planning Schedule |  |  |  |  | 108.03(g) | Weekly
YES | E. Weekly Progress Meeting, Office, and Field Laboratory Information | [8 empty] | E. Weekly Progress Meeting, Office, and Field Laboratory Information - Additional Comments
YES | 1. Day and time of weekly progress meeting:
YES | 2. Location of weekly progress meeting:
YES | 3. Field office location and set up date:
YES | 4. Field lab location and set up date:
YES | F. Legal Gross Truck Weights | [8 empty] | F. Legal Gross Truck Weights - Additional Comments
YES | Legal gross truck weights on all public roads, including within the project limits, will be controlled as follows:
YES | 1. If material is delivered to the project in a vehicle with a gross weight exceeding the legal limit, the material and the scale ticket will not be accepted. If material is inadvertently incorporated into the project, it will be price reduced per section 105.18.
YES | 2. Truck scale tickets will be delivered on site:
YES | 3. Truck scale tickets will be collected by:
YES | Submittal | [5 empty] | Specification | Due | Received
YES | IV F1 | List of Haul Vehicles |  |  |  |  | 109.01, 401.09 412.07(a) | Before delivery
YES | IV F2 | Weigher Certifications |  |  |  |  | 109.01 | Before delivery
YES | G. Environmental Product Declarations (EPDs) | [8 empty] | G. Environmental Product Declarations
YES | 1. Do the Project Specifications contain the Standard Special Provision - Revision of Sections 101 and 106 - Environmental Product Declarations | [8 empty] | Standard Special Provision - Revision of Section 101 and 106 - Environmental Product Declarations
YES |  | YES |  |  |  | NO |  |  |  | If SSP for EPD's is included check Yes and proceed with this section, if no, Skip to Section H of the Agenda.
YES | 2. Review Project Bid Items/Quanitites to determine EPD submittal requirements - See Appendix O of the Field Materials Manual | [8 empty] | See Project Plans and Appendix O of the Field Materials Manual
YES | 3. Discussion and documentation of EPD Submittal Responsibilities and timing | [8 empty] | Discuss who will be submitting (PRIME or Sub) for eligible materials EPD submittals.
YES | BID ITEM |  | EPD's Required |  | RESPONSIBLE SUBMITTER |  |  |  |  | Reference CDOT Bid Item Number and required EPD's
YES | [9 empty] | Example 503-XXXXX; EPD's required for Concrete Class BZ and Reinforcing Steel, Responsible Submitter: Prime Contractor or Sub
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES | BID ITEM |  | EPD's Required |  | RESPONSIBLE SUBMITTER
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES | [10 empty] | Phone Number - numbers only symbols not needed..
ALL | H. Fuel Cost Adjustments | [8 empty] | G. Fuel Cost Adjustments - Additional Comments
ALL | On CDOT Form 85, Contractor's Proposal submitted at the time of bid opening and per subsection 109.06 (i) Fuel Cost Adjustments, the Contractor shall chose to either accept or decline the Fuel Cost Adjustments for this project.
ALL |  | Accepts Fuel Cost Adjustments |  |  |  | Does Not Accept Fuel Cost Adjustments
ALL | The Contractor is not allowed to change this decision once bids are opened.
YES | I. Project First | [8 empty] | H. Project First - Additional Comments
YES | 1. Are the frequency, attending staff, and date of the Interim meetings scheduled?
YES | 2. Are the tools developed, i.e., Issue Documentation Matrix (aka Risk Register) and escalation ladder? Note that the Issue Documentation Matrix and Risk Register serve that same purpose and only one is needed.
YES | 3. Has an individual been assigned to maintain the tools?
YES | 4. Is an Optional Charter developed?
YES | J. Comments, Concerns, and Follow Up Items on Project Administration | [8 empty] | I. Follow Up Items on Project Administration - Additional Comments
YES
YES | V. Civil Rights & Labor Compliance | [8 empty] | V. Civil Rights & Labor Compliance - Additional Comments
YES | CDOT Personnel
YES | Region Civil Rights Specialist
YES | Name: |  |  |  |  | Office #:
ALL | Email: |  |  |  |  | Cell #:
YES | Region Civil Rights Manager
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | Contractor Personnel
YES | Contractor Project EEO Officer
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | LCPtracker Prime Approver
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | A. Civil Rights | [8 empty] | A. Civil Rights - Additional Comments
YES | 1. DBE Goal: |  |  |  | DBE Commitment:
YES | 2. On the Job Training (OJT) Goal:
YES | 3. CDOT Form 280 - EEO Interviews will be completed by CDOT Project Personnel or CDOT designee.
ALL | Number of EEO Interviews: |  |  |  |  | per month
ALL | 4. The Contractor shall submit all documents pertaining to Civil Rights and Labor Compliance to the Project Engineer and the CDOT Region Civil Rights Office.
ALL | 5. CDOT Form 205 - Sublet Permit Application shall be submitted for each Subcontractor working on the site of work per standard specification 108.01. See quick trucker guidance for applicability.
ALL | 6. CDOT Form 1425 - Supplier Application Approval Request shall to be submitted for each supplier delivering supplies to the project per standard specification 106.01. See quick trucker guidance for applicability.
YES | 7. CDOT has a zero tolerance policy against sexual harassment, workplace violence, and drug or alcohol abuse. Complaints regarding these issues should be referred to the Contractor.
YES | 8. All tiers of Subcontracts shall incorporate the FHWA 1273 - Required Contract Provisions Federal-Aid Construction Contracts for all federal aid projects.
YES | Submittal | [5 empty] | Specification | Due | Received
YES | V A1 | - Sublet Permit Application [7 Before subcontract work begins] |  |  |  |  | 108.01 | 7
YES | V A2 | Project EEO Meeting |  |  |  |  | FHWA Form 1273 | Before work completion
YES | V A3 | - Federal-Aid Highway Construction Contractors Annual EEO Report. When Contractor uses LCPtracker for payroll submission, FHWA Form 1391 is collected automatically. |  |  |  |  | Affirmative Action Requirements | Each July
YES | V A4 | Written notification to Director of Office of Federal Contract Compliance Programs for any construction subcontract in excess of $10,000 [8 by 10 business days of award of subcontract] |  |  |  |  | Affirmative Action Requirements | 8
YES | V A5 | - DBE Participation Plan Modification Request (Changing CDOT Form 1417) Approval required before change counts toward goal |  |  |  |  | DBE Req & Contract Goal | Before DBE plan change
YES | V A6 | Prompt Payment via B2GNow and based off approved CDOT Form 205s [9 Monthly and after final payment] |  |  |  |  | DBE Req & Contract Goal | 9
YES | V A7 | - Commercially Useful Function Questionnaire [10 Before retainage release] |  |  |  |  | DBE Req & Contract Goal | 10
YES | V A8 | - Supplier Application Approval Request [See VI D1] |  |  |  |  | DBE Req & Contract Goal | Before work on project |  |  | Phone Number - numbers only symbols not needed.
YES | V A9 | - Contractor Commitment to meet OJT Requirements [11 PreCon and before training begins] |  |  |  |  | OJT Training & Contract Goal | 11
YES | V A10 | - OJT Trainee/Apprentice Record & OJT training program and copy of trainee acceptance / certification approved by Engineer [12 PreCon and before training begins] |  |  |  |  | OJT Training | 12
YES | V A11 | - Trainee Status and Evaluation Report |  |  |  |  | OJT Training | Monthly
YES | V A12 | - Waiver Request for Contract's On The Job Training Hours. To count toward goal, approved before modification [13 Before OJT Goal modification] |  |  |  |  | OJT Training | 13 |  |  | Phone Number - numbers only symbols not needed.
YES | B. Bulletin Board | [8 empty] | B. Bulletin Board - Additional Comments
YES | 1. Location of Project Bulletin Board:
YES | Items posted to the bulletin board shall be legible at all times. The latest version of the documents may be obtained from the CDOT website:
YES | https://www.codot.gov/business/bidding/bulletin-board-postings
YES | C. Certified Payrolls | [8 empty] | C. Certified Payrolls - Additional Comments
YES | 1. Contractor and all applicable subcontractors shall submit their certified payrolls into LCPtracker. The employer shall pay Employees within seven days of the work ending date. Submit certified payrolls within seven days of that work ending date. The contractor shall approve payrolls within seven days after submission. All contractors and subcontractors submitting payrolls are subject to the Davis Bacon and Related Acts regulations and shall upload documentation that supports the Department of Labor approval for deductions. Failure to submit certified payrolls or associated documentation may result in the withholding of payments.
YES | 2. The Contractor Fringe Benefit Statement (CFBS) shall be submitted for each company who performs "construction work" and is required to submit certified payroll. Fringe benefits must be outlined as directed. Self-funded plans shall obtain approval from the Department of Labor. Deductions are not required to be on this fringe benefit sheet. The Contractor will follow the guidelines outlined in 29 CFR, parts 3.5 and 3.6 in order to be in compliance. Please see Guidance on Deductions for Construction Projects Requiring Certified Payrolls.
YES | D. Comments, Concerns, and Follow Up Items on Civil Rights and Labor Compliance | [8 empty] | D. Follow Up Items on Civil Rights and Labor Compliance - Additional Comments
YES | Note that a separate Civil Rights and Labor Compliance Meeting may be held to review more detailed information.
YES
YES | VI. Specialty Units | [8 empty] | VI. Specialty Units - Additional Comments
YES | A. Environmental and Wetlands | [8 empty] | A. Environmental and Wetlands - Additional Comments
YES | CDOT Personnel
YES | Region Environmental/Planning Manager
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | Contractor Personnel
YES | Contractor Erosion Control Supervisor
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | 1. Are there any restrictions in place for this project? | [5 empty] | If yes, discuss restrictions:
YES
YES | 2. All mulch, seed, sod, plants, shrubs and other similar biological material shall be free from noxious weeds to minimize their propagation. | [9 empty] | Phone Number - numbers only symbols not needed.
YES | 3. Review staked or delineated wetland areas and animal habitat areas.
YES | 4. Review protected trees and shrubs and highly erodible soils.
YES | 5. Date, time, and location of the Environmental Pre-Construction Conference Meeting:
YES
YES | 6. Review historical sites and markers within the limits of the project that are to be preserved.
YES | Submittal | [5 empty] | Specification | Due | Received
YES | VI A1 | Potential Pollution Source Report |  |  |  |  | 107.25(b)6 | PreCon
YES | VI A2 | Clean Equipment Certification |  |  |  |  | 107.25(b)21 | Before arrival
YES | VI A3 | Colorado Discharge Permit System Stormwater Construction Permit (CDPS-SCP) |  |  |  |  | 107.25(d) SSP | PreCon
YES | VI A4 | Weed Free Certification |  |  |  |  | 208.02(a), 213.02
YES | VI A5 | Concrete Washout Method Statement |  |  |  |  | 208.02(j)
YES | VI A6 | Erosion and sediment control activities in Project Schedule defined in subsection 108.03. [14 before work starts and by estimate cutoff date] |  |  |  |  | 208.03(b) | 14 |  |  | Phone Number - numbers only symbols not needed.
YES | VI A7 | Proof of Erosion Control Supervisor satisfactory completion of CDOT authorized training program. |  |  |  |  | 208.03(c)
YES | VI A8 | Spill Prevention, Control, and Countermeasure Plan |  |  |  |  | 208.06(c)
YES | VI A9 | SWMP Notebook |  |  |  |  | 208.03(d)1
YES | B. Right-of-Way | [8 empty] | B. Right-of-Way - Additional Comments
YES | CDOT Personnel
YES | Region ROW Supervisor
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | 1. Construction Surveying should be completed in accordance with Section 625 of the Contract Specifications. Ensure that all survey benchmarks, monumentation, and stakes are adequately marked and preserved.
YES | 2. Review the Limits of Construction, Historical Sites and Markers within limits, and insure that Archaeological and Paleontological Sites are staked.
YES | 3. Are there any restrictions in place for this project? | [5 empty] | If yes, discuss restrictions:
YES
YES | 4. Agreements to Access Private Property The Contractor shall furnish the Project Engineer properly executed written documentation from property owners that authorizes the Contractor to trespass on private property for any of the following conditions: a. Temporary livestock fencing outside the ROW b. Not installing livestock fencing and who will be held responsible until fence is installed c. Haul roads on private property not designated on the plans d. Waste or stockpile areas on private property not designated on the plans e. Equipment, camp, plant, or crusher sites on private property not designated on the plans f. Sources of aggregates, borrow, etc. on private property not designated on the plans. Comments:
YES
YES | 5. Visual aids can substantially complement the written documentation required by CDOT especially in verifying existing site conditions. Before and during the project, use photographs and video recordings to document field conditions and progress.
YES | C. Utilities | [8 empty] | C. Utilities - Additional Comments | Phone Number - numbers only symbols not needed.
YES | CDOT Personnel
YES | Region Utilities Engineer
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | Utility Personnel - And Discussion of Restrictions or Conflicts
YES | Electric:
YES | Company: |  |  |  |  | Office #:
YES | Name: |  |  |  |  | Title:
YES | Email: |  |  |  |  | Cell #:
YES
YES
YES | Gas:
YES | Company: |  |  |  |  | Office #:
YES | Name: |  |  |  |  | Title:
YES | Email: |  |  |  |  | Cell #:
YES
YES
YES | Telephone: | [9 empty] | Phone Number - numbers only symbols not needed.
YES | Company: |  |  |  |  | Office #:
YES | Name: |  |  |  |  | Title:
YES | Email: |  |  |  |  | Cell #:
YES
YES
YES | Water:
YES | Company: |  |  |  |  | Office #:
YES | Name: |  |  |  |  | Title:
YES | Email: |  |  |  |  | Cell #:
YES
YES
YES | Sewer:
YES | Company: |  |  |  |  | Office #:
YES | Name: |  |  |  |  | Title:
YES | Email: |  |  |  |  | Cell #:
YES
YES
YES | Cable: | [9 empty] | Phone Number - numbers only symbols not needed.
YES | Company: |  |  |  |  | Office #:
YES | Name: |  |  |  |  | Title:
YES | Email: |  |  |  |  | Cell #:
YES
YES
YES | ITS:
YES | Company: |  |  |  |  | Office #:
YES | Name: |  |  |  |  | Title:
YES | Email: |  |  |  |  | Cell #:
YES
YES
YES | Railroad:
YES | Company: |  |  |  |  | Office #:
YES | Name: |  |  |  |  | Title: |  |  |  |  | Phone Number - numbers only symbols not needed.
YES | Email: |  |  |  |  | Cell #:
YES
YES
YES | Irrigation:
YES | Company: |  |  |  |  | Office #:
YES | Name: |  |  |  |  | Title:
YES | Email: |  |  |  |  | Cell #:
YES
YES
YES | Other: | [9 empty] | Phone Number - numbers only symbols not needed.
YES | Company: |  |  |  |  | Office #:
YES | Name: |  |  |  |  | Title:
YES | Email: |  |  |  |  | Cell #:
YES
YES
YES | D. Materials | [8 empty] | D. Materials - Additional Comments
YES | CDOT Personnel
YES | CDOT Quality Assurance Supervisor/Head Tester
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | CDOT Project Tester
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | Region Materials Engineer
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | Contractor Personnel
YES | Contractor Quality Assurance Personnel
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | Agenda Items
YES | 1. The Contractor should reference the submittal list and the CDOT Approved Product List (APL) to know which documents are required to be submitted. The APL list can be accessed at https://www.codot.gov/business/apl/notice-to-contractors.html.
YES | 2. Mix Designs and Material Samples - Required mix designs are shown on the submittals list. Any unapproved materials shall not be placed on the project. The Contractor shall reference the "Special Notice to Contractors" in the CDOT Field Materials Manual for information concerning timely submittal of material samples.
YES | 3. Land Reclamation Pit - The Contractor shall comply with the requirements of the Land Reclamation Permit, including pit limits. Comments:
YES
YES | 4. Test Data will be available for the Contractor's review on a daily basis. The CDOT Form 626 - Field Lab Tests Results will be given to the Contractor for failing tests. If required, who on the Contractor's staff shall receive this form?
YES
YES | 5. The Certificates of Compliance (COCs) and Certified Test Reports (CTRs) shall contain the eleven items shown in Subsection 106.12 and 106.13 respectively and the following statement with an original signature and date: "I hereby certify under penalty of perjury that the material listed in this Certificate of Compliance/Certified Test Report represents (QUANTITY) of pay item (PAY ITEM NUMBER & DESCRIPTION) for installation on project number (PROJECT NUMBER)."
YES | 6. Certified Invoices shall contain the following statement with an original signature and date: "I certify, by this invoice, that the quantity of material/rental or lease/specialty work, represented by this invoice was purchased and received for CDOT Project No. (PROJECT NUMBER) and that the prices shown are actual costs."
YES | 7. Salvable Materials that become the property of CDOT shall be carefully removed in sections and properly marked and stored. Where required, the Contractor is to utilize match markings for the reassembly of structures. If materials are to be reused on the project, they will be inspected for damage after they are removed. Discuss any special requirements as per Project Provisions.
YES | 8. The Contractor shall follow all requirements outlined in the contract regarding Buy America. Failure to comply will result in removal of the non-complaint steel or iron at the Contractor's expense. Note that all required documentation for the Buy America program shall be received before fabrication or installation. Refer to subsection 206.11 of the Specifications for this Project). Comments:
YES
YES | Submittal | [5 empty] | Specification | Due | Received
YES | VI D1 | - Supplier Application Approval Request [See V A8][15PreCon & update 2 weeks before delivery or fabrication of material] |  |  |  |  | 106.01 | 15
YES | VI D2 | Source of Undesignated Materials [16Before each item is used on project] |  |  |  |  | 106.02(b) | 16
YES | VI D3 | Pipe Material to be used |  |  |  |  | 624.02 | PreCon
YES | VI D4 | What Structural Plate Material will be used - Aluminum or Steel? |  |  |  |  | 510.02 | PreCon
YES | VI D5 | Water Stops and Expansion Joints - manufacturer and model number of designated devices |  |  |  |  | 518.04, 518.05, 518.07 | PreCon
YES | VI D6 | Lighting materials and equipment |  |  |  |  | 613.02(i) | PreCon
YES | VI D7 | Concrete Mix Design |  |  |  |  | 601.05 | For approval before placement |  |  | Phone Number - numbers only symbols not needed.
YES | VI D8 | Certified Cement Test Reports |  |  |  |  | 106.13, 601.05, 701.01 | Before use of cement
YES | VI D9 | Certified Fly Ash Test Reports |  |  |  |  | 106.13, 601.05, 701.01 | Before use of fly ash
YES | VI D10 | Flow fill Mix Design |  |  |  |  | 206.02(a) | For approval before placement
YES | VI D11 | Concrete Quality Control Plan |  |  |  |  | 106.06(a)1 | PreCon
YES | VI D12 | - Concrete Truck Mixer Inspection Certification [17When each concrete truck is delivering to site] |  |  |  |  | 601.07(c)3 | 17
YES | VI D13 | Scale Certifications |  |  |  |  | 109.01 | When truck is delivering to site
YES | VI D14 | HMA Mix Design |  |  |  |  | 401.02(a)1 | For approval before mix production
YES | VI D15 | HMA Quality Control Plan |  |  |  |  | 106.05(a)1 | PreCon
YES | VI D16 | HMA Segregation Quality Control Plan |  |  |  |  | 403.02 PSP | For approval before paving
YES | VI D17 | NCHRP 350 Certification for Work Zone Devices [18 Before each items is used on project] |  |  |  |  | 630.09 | 18
YES | VI D18 | COCs |  |  |  |  | 106.12 | Before installation
YES | VI D19 | CTRs |  |  |  |  | 106.13 | Before installation
YES | VI D20 | Paint Certification |  |  |  |  | 708 | Before use
YES | VI D21 | Quality Control Plan for Embankment |  |  |  |  | 203.03(a) | For approval before placement
YES | VI D22 | Buy America Certification [19 Before permanent incorporation of steel or iron on project] |  |  |  |  | 106.11 | 19
YES | E. Hydraulics | [8 empty] | E. Hydraulics - Additional Comments
YES | CDOT Personnel
YES | Region Hydraulics Engineer
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | 1. Are there any restrictions in place for this project? | [5 empty] | If yes, discuss restrictions:
YES
ALL | F. Staff Bridge | [8 empty] | F. Staff Bridge - Additional Comments
ALL | CDOT Personnel
ALL | CDOT Staff Bridge Unit Leader | [9 empty] | Phone Number - numbers only symbols not needed.
ALL | Name: |  |  |  |  | Office #:
ALL | Email: |  |  |  |  | Cell #:
ALL | CDOT Bridge Construction Engineer
ALL | Name: |  |  |  |  | Office #:
ALL | Email: |  |  |  |  | Cell #:
ALL | 1. Are there any restrictions in place for this project? | [5 empty] | If yes, discuss restrictions:
ALL
ALL | 2. Fabrication Quality Assurance Inspection required from Staff Bridge?
ALL | Submittal | [5 empty] | Specification | Due | Received
ALL | VI F1 | Erection Plan, Precast Bridge Girders and Falsework - Review from CDOT Bridge Fabrication Unit [20By 1 week before Pre-Erection Conference or 2 weeks before fabrication] |  |  |  |  | 509.27, 601.11, 618.14 | 20
ALL | VI F2 | Written documentation of daily inspections of the erected girders and other permanent and temporary bridge elements until the deck concrete has attained the Field Compressive Strength. |  |  |  |  | 509.27, 601.11, 618.14 | Within 24 hours after inspection
ALL | VI F3 | Shop drawings for all prestressed components |  |  |  |  | 618.04 | With Erection Plan
ALL | VI F4 | Shop drawings, design calculations and load data for review of Type III bearing devices |  |  |  |  | 512.17 | With Erection Plan
ALL | G. Comments, Concerns, and Follow Up Items on Specialty Units: | [8 empty] | G. Follow Up Items on Specialy Units - Additional Comments
ALL
ALL | VII. Safety | [8 empty] | VII. Safety - Additional Comments
ALL | CDOT Personnel
ALL | Region Safety Officer
ALL | Name: |  |  |  |  | Office #:
ALL | Email: |  |  |  |  | Cell #:
ALL | Contractor Personnel
ALL | Contractor Safety Officer | [9 empty] | Phone Number - numbers only symbols not needed.
ALL | Name: |  |  |  |  | Office #:
ALL | Email: |  |  |  |  | Cell #:
ALL | A. Submittals | [8 empty] | A. Submittals - Additional Comments
ALL | 1. The Contractor should reference the submittal list to know which documents are required to be submitted.
ALL | 2. The Contractor shall conduct field safety meetings (also known as Toolbox or Tailgate meetings) at the frequency specified in the Plan, which shall be at least once per week.
ALL | 3. The Contractor shall fill out the Notification for Serious Accident or Event on Construction Projects for any fatality, major injury (life threatening), or if 2 or more people are injured (non-life threatening) within the work zone.
ALL | 4. The Contractor will be allowed to resume operations only after providing written documentation, certified by the Project Safety Manager or alternate, regarding the corrective actions taken to prevent recurrence. See Standard Specifications 107.06(f). Comments:
ALL
ALL | Submittal | [5 empty] | Specification | Due | Received
ALL | VII A1 | Health and Safety Plan (HASP) - including First Aid/Hospital/EMT Statement |  |  |  |  | 250.03(c) | For approval before construction
ALL | VII A2 | - Emergency Phone Number Cards to be posted on job site |  |  |  |  | included in this agenda | PreCon
ALL | VII A3 | Project Safety Management Plan |  |  |  |  | 107.06(a) | Before construction |  |  | Phone Number - numbers only symbols not needed.
ALL | VII A4 | Safety "Toolbox" Meeting Schedule |  |  |  |  | 107.06(a)4 | Before construction
NO | VII A5 | PPE Statement |  |  |  |  | 107.06(e), 250.03(d)2F | Before construction
NO | B. Construction Zone Traffic Control | [8 empty] | B. Construction Zone Traffic Control - Additional Comments
NO | Contractor Personnel
YES | Traffic Control Company:
YES | (Traffic Control Company Name Here)
YES | Address: |  |  |  |  | Office #:
YES | Traffic Control Supervisor
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | 1. The Contractor's Superintendent and all others serving in a similar capacity are required to complete a CDOT-approved two-day Traffic Control Supervisor training.
YES | 2. NCHRP 350 Requirements shall be met and fully implemented.
YES | Submittal | [5 empty] | Specification | Due | Received
YES | VII B1 | Traffic Control Certifications for all personnel handling traffic including Superintendent and TCS |  |  |  |  | 630.11 | PreCon
YES | VII B2 | NCHRP, Test Level 3 Certification for all Traffic Control Devices to be used on project |  |  |  |  | 630.10(a) | PreCon with initial TMP
YES | C. Transportation Management Plan (TMP) | [8 empty] | C. Transportation Management Plan (TMP) - Additional Comments
YES | CDOT Personnel
YES | Region Communications Manager
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | Consultant Public Information Manager
YES | Name: |  |  |  |  | Office #: |  |  |  |  | Phone Number - numbers only symbols not needed.
YES | Email: |  |  |  |  | Cell #:
YES | Contractor Personnel
YES | Public Information Manager
YES | Name: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | 1. Is this project considered a Significant Project? (Most projects are Significant and this is shown on the plans.)
YES | If so, has the TMP been submitted including the TCP, To, and PIP?
YES | The Contractor shall prepare a TMP for each phase of the project.
YES | Submittal | [5 empty] | Specification | Due | Received
ALL | VII C1 | Transportation Management Plan (TMP) - Initial Plan provided at PreCon |  |  |  |  | 630.1 | For approval before each phase
ALL | VII C2 | Traffic Control Plan (TCP) |  |  |  |  | 630.10(a) | with TMP
ALL | VII C3 | Transportation Operations Plan (TO) |  |  |  |  | 630.10(b) | with TMP & weekly
ALL | VII C4 | Public Information Manager (PIM) credentials and Public Information Management Plan (PIP) |  |  |  |  | 630.10, 626 | PreCon with initial TMP
ALL | VII C5 | Stakeholder list |  |  |  |  | 626 | with PIP
ALL | VII C6 | Specific Stakeholders needing ongoing communication |  |  |  |  | 626 | with PIP
ALL | Other Stakeholders
ALL | Organization:
ALL | Name: |  |  |  |  | Title:
ALL | Address: |  |  |  |  | Office #:
ALL | Email: |  |  |  |  | Cell #:
ALL | Organization:
YES | Name: |  |  |  |  | Title:
YES | Address: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | Organization:
YES | Name: |  |  |  |  | Title:
YES | Address: |  |  |  |  | Office #:
YES | Email: |  |  |  |  | Cell #:
YES | D. Method of Handling Traffic (MHT) - Initial submittal required at PreCon | [8 empty] | D. Method of Handling Traffic (MHT) - Additional Comments
YES | 1. Does the MHT contain a detailed diagram showing the location of all traffic control devices?
ALL | 2. Does the MHT show the method, length, and time duration for lane closures?
ALL | 3. Does the MHT show the location of flaggers and time duration of flagging operation?
ALL | 4. Doe the MHT contain a tabulation of all traffic control devices?
ALL | 5. Does the MHT address details of a mobile pavement marking zone (as required by the contract)
ALL | 6. Does the MHT list supporting references?
ALL | 7. Does the MHT show an access maintenance plan showing access for all properties?
ALL | 8. Does the MHT show areas where equipment will be stored, vehicles parked, and construction signs and materials will be stored?
YES | 9. Does the MHT have a plan for maintaining and controlling pedestrian, bicycle, and other non-vehicular traffic?
YES | 10. Are verifications needed by survey of horizontal or vertical clearances?
YES | Comments:
YES | Submittal | [5 empty] | Specification | Due | Received
YES | VII D1 | Method of Handling Traffic (MHT) to implement TCP - Initial MHT with TMP provided at PreCon |  |  |  |  | 630.10(a) | For approval before use
YES | VII D2 | Construction Traffic Information Signs |  |  |  |  | S-630-1 note 6 | after Award
YES | E. Construction Signing | [8 empty] | E. Construction Signing - Additional Comments
YES | 1. All signing shall conform to the latest adopted version of the MUTCD, including the Colorado Supplement.
YES | The current MUTCD can be found at: https://mutcd.fhwa.dot.gov/pdfs/2009r1r2/pdf_index.htm.
YES | The Colorado Supplement can be found at: https://www.codot.gov/safety/traffic-safety/assets/documents/mutcd/MUTCD_2003_Colorado_Supplement.pdf
YES | 2. Is there any construction signing on the project that is not the responsibility of the Contractor?
YES | If yes, whom is responsible?
YES | F. Speed Limits/Uniform Traffic Control | [8 empty] | F. Speed Limits/ Uniform Traffic Control - Additional Comments
ALL | 1. Has the Form 568 has been approved based on plans and specifications
ALL | for a reduction of speed to |  |  |  | MPH
YES | 2. Uniform Traffic Control (UTC) will be utilized on this project.
YES | The Contractor shall conform to and submit a copy of the local jurisdiction's policy regarding authorized duties of the UTC on the project
YES | Submittal | [5 empty] | Specification | Due | Received
YES | VII F1 | Form 568 - Authorization and Declaration of Temporary Speed Limits |  |  |  |  | 630.13, S-630-1 note 3 | Before use
YES | G. Restrictions (Performed by Project Engineer) | [8 empty] | G. Restrictions (Performed by Project Engineer) - Additional Comments
YES | 1. Oversize/Overweight Vehicles
YES | Is there an over size or overweight restriction needed for vehicles on this project?
YES | If oversize/ overweight or vertical/horizontal restrictions are required, the Project Engineer will submit the following information to the Permits Unit of the Maintenance and Operations Branch at least 10 days in advance of the restriction.
YES | 2. Vertical and/or Horizontal Restrictions
YES | Is there a vertical or horizontal restrictions needed for vehicles on this project?
YES | If over size / overweight or vertical / horizontal restrictions are required, the Project Engineer will submit the following information to the Permits Unit of the Maintenance and Operations Branch at least 10 days in advance of the restriction.
YES | Start Date of Restriction: |  |  |  |  | Width:
YES | End Date of Restriction: |  |  |  |  | Length:
ALL | Highway: |  |  |  |  | Town:
ALL | Begin Milepost: |  |  |  |  | Junction:
ALL | End Milepost: |  |  |  |  | Restriction:
ALL | Junction: |  |  |  |  | Other:
ALL | H. Hazardous Materials & Operations | [8 empty] | H. Hazardous Materials & Operations - Additional Comments
ALL | Ensure that all suspected hazardous material and hazardous waste sites that have been identified during the Modified Environmental Site Assessment and Site Investigation are properly staked or otherwise delineated. All special requirements of the Contract shall be strictly enforced. Hazardous materials include lead paint, methamphetamine by-products, and lab waste (death bags), etc. If anyone suspects hazardous materials on their projects they should immediately notify the Project Engineer. The Contractor is solely responsible for adhering to Federal and State laws and local ordinances with respect to the safety of project personnel and the general public.
ALL | I. Comments, Concerns, and Follow Up Items on Safety: | [8 empty] | I. Follow Up Items on Safety - Additional Comments
ALL
ALL | VIII. Other Items | [8 empty] | VIII. Other Items - Additional Comments
YES | A. Items of Note:
YES | Are there any Project Special Provisions that should be discussed?
YES | Comments: | [9 empty] | Date Format: MM/DD/YYYY Time Format: HH:MM AM/PM
YES | B. Contractor Comments:
YES | Does the Contractor have any additional concerns/comments not previously discussed in this meeting?
YES | Comments:
YES | C. Uncomplete Items Before Starting Work:
YES
YES | D. Possible Change Orders:
YES
YES | E. Contractor Evaluation: | [8 empty] | E. Contractor Evaluation - Additional Comments
YES | After Project Completion, the Engineer will evaluate the Contractor in accordance with the Project Evaluation System (PES). The Project Engineer will fill out the evaluation and submit the results within PES. PES will automatically forward this evaluation to the contractor for concurrence and comment. If the Contractor has comments about the Project Engineer’s evaluation, Contact the Resident Engineer will review to render a final decision. A project score is an “evaluation.”. The five most recent project specific evaluations will be averaged to calculate a “rating.”
YES | Score |  | Grade | Action on Evaluation |  |  | Action on Rating
YES | 15 and higher |  | A | None |  |  | None
YES | 5 TO 14 |  | B | None |  |  | None
| -5 TO 4 |  | C | None |  |  | Warning
| -6 TO -15 |  | D | Warning |  |  | Lower Prequalification
| -16 and lower |  | F | Suspension |  |  | Suspension
If requested by the Contractor, the Project Engineer shall provide at least one interim evaluation during construction of the project. It is at the discretion of the Project Engineer as to how many other interim evaluations may be provided. Interim evaluations will not go in the PES database but shall kept in the project files. PES will also send an email to the contractor requesting the contractor fill out an evaluation of CDOT. This project evaluation will include, among other things, an evaluation of the design (plans and specs) and an evaluation of CDOT’s construction staff. PES will forward these evaluation results to the Resident Engineer.
| IX. Additional Meeting List | [8 empty] | IX. Additional Meeting List - Additional Comments
| Meeting |  |  | Date |  | Time | Location and Comments
Project First Workshop
Pre-Survey Conference
Asphalt Pre-Paving and QC/QA
Concrete Pre-Paving
Pre-Erection
Environmental PreCon Conference
Schedule Review Meeting
Weekly Progress Meeting
Standing DRB Update Meeting
Civil Rights & Labor Compliance
CDOT Form 205
FHWA Form 1391
CDOT Form 1420
CDOT Form 1432
CDOT Form 1425
CDOT Form 1337
CDOT Form 838
CDOT Form 832
CDOT Form 1336
Form 1425
Form 46
Form 140

## Emergency Notification
Emergency Notification List
Date Updated: |  |  | 2022-07-27 11:33
Project Code: |  |  | 0 | [5 empty] | Project Number: |  |  | 0
Description:
0
Location (route, begin milepost, and end milepost):
0
Estimated Construction
Start Date: |  |  | 0 |  |  |  | End Date: |  |  | 0
CDOT
Project Engineer |  |  |  |  | Resident Engineer | [5 empty] | Maintenance Supervisor
Name: |  | 0 |  |  | Name: |  | 0 |  |  |  | Name: |  | 0
Email: |  | 0 |  |  | Email: |  | 0 |  |  |  | Email: |  | 0
Office # |  | 0 |  |  | Office # |  | 0 |  |  |  | Office # |  | 0
Cell # |  | 0 |  |  | Cell # |  | 0 |  |  |  | Cell # |  | 0
Contractor
Address: |  | 0 | [8 empty] | Office # |  | 0
Project Manager |  |  |  |  | Superintendent | [5 empty] | Alternate Superintendent 1
Name: |  | 0 |  |  | Name: |  | 0 |  |  |  | Name: |  | 0
Email: |  | 0 |  |  | Email: |  | 0 |  |  |  | Email: |  | 0
Office # |  | 0 |  |  | Office # |  | 0 |  |  |  | Office # |  | 0
Cell # |  | 0 |  |  | Cell # |  | 0 |  |  |  | Cell # |  | 0
Traffic Control Contractor
Traffic Control Company: |  |  |  | (Traffic Control Company Name Here)
Address: |  | 0 | [8 empty] | Office # |  | 0
|  | Traffic Control Supervisor | [6 empty] | Alternate TCS
Name: |  | 0 | [5 empty] | Name:
Email: |  | 0 | [5 empty] | Email:
Office #: |  | 0 | [5 empty] | Office #:
Cell #: |  | 0 | [5 empty] | Cell #:
cc: | State Patrol Dispatch |  |  | RTD |  | Program Engineer |  |  |  | Region Materials |  |  |  | RSO
| Local State Patrol |  |  | RCM |  | Resident Engineer |  |  |  | Region Civil Rights |  |  |  | TCS
| Local Sheriff/Police |  |  | PIM |  | Maintenance Supt. |  |  |  | Finals Administrator |  |  |  | File

## Form 140 Emergency Numbers
EMERGENCY PHONE NUMBERS
Physician | 0 | or | 0
Hospital | 0 | or | 0
Ambulance | 0 | or | 0
Fire | 0 | or | 0
Police | 0 | or | 0
CDOT Form No. 140 [1/93]

## Submittal List
Include? | 0 |  |  | 0
YES | Submittal |  | Specification | Due | Received?
YES | IV A1 | Form 1378 - Contractor Selection of Litigation or Arbitration | 105.24(f) | PreCon | 0
YES | IV A2 | Form 1379 - Dispute Review Board Three Party Agreement for Standing Board | 105.23(b) | By 15 days of Contract Execution | 0
ALL | IV B1 | Initial Payment Schedule | 108.04(a) | BY 15 days of Award | 0
ALL | IV B2 | Payment Schedule Updates | 108.04(b) | 1st of month | 0
ALL | IV B3 | Payment/Drawdown Schedule Update | 108.04(b) | 1st of month | 0
ALL | IV D1 | Baseline Schedule or Preliminary Schedule [*and approved before work starts] | 108.03(c) 108.03(d) or (e) | By 14 days after Award* | 0
ALL | IV D2 | Scheduling Software Selection - Microsoft Project or Oracle Primavera | 108.03(b) | By 14 days after Award | 0
ALL | IV D3 | When Preliminary Schedule submitted full Baseline Schedule [*and approved before continuing past first 60 days] | 108.03(c) 108.03(e) | By 45 days after Award* | 0
ALL | IV D4 | Project Schedule Update including time-scaled logic diagram, native software file (xer or mpp), and reports | 108.03(c) 108.03(f) | By each estimate cutoff date | 0
ALL | IV D5 | Weekly Planning Schedule | 108.03(g) | Weekly | 0
YES | IV F1 | List of Haul Vehicles | 109.01, 401.09, 412.07(a) | Before delivery | 0
YES | IV F2 | Weigher Certifications | 109.01 | Before delivery | 0
YES | V A1 | - Sublet Permit Application | 108.01 | Before subcontract work begins | 0
YES | V A2 | Project EEO Meeting | FHWA Form 1273 | Before work completion | 0
YES | V A3 | - Federal-Aid Highway Construction Contractors Annual EEO Report. When contractor uses LCPtracker for payroll submission, FHWA Form 1391 will be collected automatically. | Affirmative Action Requirements | Each July | 0
YES | V A4 | Written notification to Director of Office of Federal Contract Compliance Programs for any construction subcontract in excess of $10,000 | Affirmative Action Requirements | By 10 business days of award of subcontract | 0
YES | V A5 | - DBE Participation Plan Modification Request (Changing CDOT Form 1417) Approval required before change counts toward goal | DBE Requirements & Contract Goal | Before changing DBE Plan | 0
YES | V A6 | Prompt Payment via B2GNow and based off approved CDOT Form 205s | DBE Requirements & Contract Goal | Monthly and after final payment | 0
YES | V A7 | - Commercially Useful Function Questionnaire | DBE Requirements & Contract Goal | Before retainage release | 0
YES | V A8 | - Supplier Application Approval Request [See VI D1] | DBE Requirements & Contract Goal | Before work on project | 0
YES | V A9 | - Contractor Commitment to Meet OJT Requirements | OJT Training & Contract Goal | PreCon and before training begins | 0
YES | V A10 | - OJT Trainee/Apprentice Record & OJT training program and copy of trainee acceptance / certification approved by Engineer | OJT Training | PreCon and before training begins | 0
YES | V A11 | - Trainee Status and Evaluation Report | OJT Training | Monthly | 0
YES | V A12 | - Waiver Request for Contract's On The Job Training Hours. To count toward goal, approved before modification | OJT Training | Before changing Goal | 0
YES | VI A1 | Potential Pollution Source Report | 107.25(b)6 | PreCon | 0
YES | VI A2 | Clean Equipment Certification | 107.25(b)21 | Before arrival | 0
YES | VI A3 | Colorado Discharge Permit System Stormwater Construction Permit (CDPS-SCP) | 107.25(d) SSP | PreCon | 0
YES | VI A4 | Weed Free Certification | 208.02(a), 213.02 |  | 0
YES | VI A5 | Concrete Washout Method Statement | 208.02(j) |  | 0
YES | VI A6 | Erosion and sediment control activities in Project Schedule defined in subsection 108.03 | 208.03(b) | before work starts & by estimate cutoff date | 0
YES | VI A7 | Proof of Erosion Control Supervisor satisfactory completion of CDOT authorized training program | 208.03(c) |  | 0
YES | VI A8 | Spill Prevention, Control, and Countermeasure Plan | 208.06(c) |  | 0
YES | VI A9 | SWMP Notebook | 208.03(d)1 |  | 0
YES | VI D1 | - Supplier Application Approval Request [See V A8] | 106.01 | At PreCon & 2 weeks before delivery or fabrication of material | 0
YES | VI D2 | Source of Undesignated Materials | 106.02(b) | Before each item is used | 0
YES | VI D3 | Pipe Material to be used | 624.02 | PreCon | 0
YES | VI D4 | What Structural Plate Material will be used - Aluminum or Steel? | 510.02 | PreCon | 0
YES | VI D5 | Water Stops and Expansion Joints - manufacturer and model number of designated devices | 518.04, 518.05, 518.07 | PreCon | 0
YES | VI D6 | Lighting materials and equipment | 613.02(i) | PreCon | 0
YES | VI D7 | Concrete Mix Design | 601.05 | For approval before placement | 0
YES | VI D8 | Certified Cement Test Reports | 106.13, 601.05, 701.01 | Before use of cement | 0
YES | VI D9 | Certified Fly Ash Test Reports | 106.13, 601.05, 701.01 | Before use of fly ash | 0
YES | VI D10 | Flow fill Mix Design | 206.02(a) | For approval before placement | 0
YES | VI D11 | Concrete Quality Control Plan | 106.06(a)1 | PreCon | 0
YES | VI D12 | - Concrete Truck Mixer Inspection Certification | 601.07(c)3 | When concrete truck delivers to site | 0
YES | VI D13 | Scale Certifications | 109.01 | When truck delivers to site | 0
YES | VI D14 | HMA Mix Design | 401.02(a)1 | For approval before mix production | 0
YES | VI D15 | HMA Quality Control Plan | 106.05(a)1 | PreCon | 0
YES | VI D16 | HMA Segregation Quality Control Plan | 403.02 | For approval before paving | 0
YES | VI D17 | NCHRP 350 Certification for Work Zone Devices | 630.09 | For each item before used | 0
YES | VI D18 | COCs | 106.12 | Before installation | 0
YES | VI D19 | CTRs | 106.13 | Before installation | 0
YES | VI D20 | Paint Certification | 708 | Before use | 0
YES | VI D21 | Quality Control Plan for Embankment | 203.03(a) | For approval before placement | 0
YES | VI D22 | Buy America Certification | 106.11 | Before incorporation | 0
YES | VI F1 | Erection Plan, Precast Bridge Girders, and Falsework - Review from CDOT Bridge Fabrication Unit | 509.27, 601.11, 618.14 | 1 week before pre-erection conference or 2 weeks before fabrication | 0
YES | VI F2 | Written daily inspections of erected girders and permanent and temporary bridge elements until deck concrete reaches Field Compressive Strength | 509.27, 601.11, 618.14 | Within 24 hours after inspection | 0
YES | VI F3 | Shop drawings for all prestressed components | 618.04 | With Erection Plan | 0
YES | VI F4 | Shop drawings, design calculations, and load data for review of Type III bearing devices | 512.17 | With Erection Plan | 0
ALL | VII A1 | Health and Safety Plan (HASP) - including First Aid/Hospital/EMT Statement | 250.03(c) | For approval before construction | 0
ALL | VII A2 | - Emergency Phone Number Cards to be posted on job site | included in this agenda | PreCon | 0
ALL | VII A3 | Project Safety Management Plan | 107.06(a) | Before construction | 0
ALL | VII A4 | Safety "Toolbox" Meeting Schedule | 107.06(a)4 | Before construction | 0
ALL | VII A5 | PPE Statement | 107.06(e), 250.03(d)2F | Before construction | 0
ALL | VII B1 | Traffic Control Certifications for all personnel handling traffic including Superintendent and TCS | 630.11 | PreCon | 0
ALL | VII B2 | NCHRP, Test Level 3 Certification for all Traffic Control Devices to be used on project | 630.10(a) | PreCon with initial TMP | 0
YES | VII C1 | Transportation Management Plan (TMP) - Initial Plan provided at PreCon | 630.1 | PreCon and before each phase | 0
YES | VII C2 | Traffic Control Plan (TCP) | 630.10(a) | with TMP | 0
YES | VII C3 | Transportation Operations Plan (TO) | 630.10(b) | with TMP & weekly | 0
YES | VII C4 | Public Information Manager (PIM) credentials and Public Information Management Plan (PIP) | 630.10, 626 | PreCon with initial TMP | 0
YES | VII C5 | Stakeholder list | 626 | with PIP | 0
YES | VII C6 | Specific Stakeholders needing ongoing communication | 626 | with PIP | 0
YES | VII D1 | Method of Handling Traffic (MHT) to implement TCP - Initial MHT with TMP | 630.10(a) | PreCon and before each phase | 0
YES | VII D2 | Construction Traffic Information Signs | S-630-1 note 6 | After Award | 0
ALL | VII F1 | Form 568 - Authorization and Declaration of Temporary Speed Limits | 630.13, S-630-1 note 3 | Before use | 0
CDOT Form 205
FHWA Form 1391
CDOT Form 1420
CDOT Form 1432
CDOT Form 1425
CDOT Form 1337
CDOT Form 838
CDOT Form 832
CDOT Form 1336
CDOT Form 1425
Form 46
Form 140

## Project Personnel
Include? | 0 |  | 0
ALL | CDOT Personnel
ALL | Project Engineer
ALL | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
ALL | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
NO | Assistant Project Engineer
NO | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
NO | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
YES | Inspector 1
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
NO | Inspector 2
NO | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
NO | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
NO | Inspector 3
NO | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
NO | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
ALL | Resident Engineer
ALL | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
ALL | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
ALL | Maintenance Representative
ALL | Name: | 0 |  |  |  | Office #: | 0
ALL | Email: | 0 |  |  |  | Cell #: | 0
YES | Region Civil Rights Specialist
YES | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
#REF! | Email: | 0 |  |  |  | Cell #: | 0 | 0 | 0
#REF! | Region Civil Rights Manager
#REF! | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
#REF! | Email: | 0 |  |  |  | Cell #: | 0 | 0 | 0
YES | Region Environmental/Planning Manager
YES | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
YES | Email: | 0 |  |  |  | Cell #: | 0 | 0 | 0
YES | Region ROW Supervisor
YES | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
YES | Email: | 0 |  |  |  | Cell #: | 0 | 0 | 0
YES | Region Utilities Engineer
YES | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
YES | Email: | 0 |  |  |  | Cell #: | 0 | 0 | 0
YES | CDOT Quality Assurance Supervisor/Head Tester
YES | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
YES | Email: | 0 |  |  |  | Cell #: | 0 | 0 | 0
YES | CDOT Project Tester
YES | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
YES | Email: | 0 |  |  |  | Cell #: | 0 | 0 | 0
YES | Region Materials Engineer
YES | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
YES | Email: | 0 |  |  |  | Cell #: | 0 | 0 | 0
YES | Region Hydraulics Engineer
YES | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
YES | Email: | 0 |  |  |  | Cell #: | 0 | 0 | 0
YES | CDOT Staff Bridge Unit Leader
YES | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
YES | Email: | 0 |  |  |  | Cell #: | 0 | 0 | 0
YES | CDOT Bridge Construction Engineer
YES | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
YES | Email: | 0 |  |  |  | Cell #: | 0 | 0 | 0
ALL | Region Safety Officer
ALL | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
ALL | Email: | 0 |  |  |  | Cell #: | 0 | 0 | 0
ALL | Region Communications Manager
ALL | Name: | 0 |  |  |  | Office #: | 0 | Pre-Con | 0
ALL | Email: | 0 |  |  |  | Cell #: | 0 | by 15 days of Contract Execution | 0
NO | Consultant Public Information Manager
NO | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
NO | Email: | 0 |  |  |  | Cell #: | 0 | 0 | 0
ALL | Contractor Personnel
ALL | (Contractor Company Name Here)
ALL | Address: | 0 |  |  |  | Phone: | 0
YES | Project Manager
YES | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
ALL | Superintendent
ALL | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
ALL | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
NO | Alternate Superintendent 1
NO | Name: | 0 |  |  |  | Office #: | 0 | 1st of Month | 0
NO | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 1st of Month | 0
NO | Alternate Superintendent 2
NO | Name: | 0 |  |  |  | Office #: | 0 | 0 | days or date
NO | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
NO | Other
NO | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
NO | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
ALL | Contractor Project EEO Officer
ALL | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
ALL | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
YES | LCPtracker Prime Approver
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
YES | Contractor Erosion Control Supervisor
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
YES | Contractor Quality Assurance Personnel
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
ALL | Contractor Safety Officer
ALL | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
ALL | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
ALL | Traffic Control Company:
ALL | (Traffic Control Company Name Here)
ALL | Address: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
ALL | Traffic Control Supervisor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ALL | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
ALL | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
YES | Public Information Manager
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
NO | Local Agency Representatives
NO | (Local Agency Name Here)
NO | Name: | 0 |  |  |  | Office #: | 0
NO | Email: | 0 |  |  |  | Cell #: | 0
NO | (Local Agency Name Here)
NO | Name: | 0 |  |  |  | Office #: | 0
NO | Email: | 0 |  |  |  | Cell #: | 0
NO | (Local Agency Name Here)
NO | Name: | 0 |  |  |  | Office #: | 0
NO | Email: | 0 |  |  |  | Cell #: | 0
ALL | Utilities
YES | Electric:
YES | Company: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
YES | Gas:
YES | Company: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
YES | Telephone:
YES | Company: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
YES | Water:
YES | Company: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
YES | Sewer:
YES | Company: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
YES | Cable:
YES | Company: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
YES | ITS:
YES | Company: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
YES | Railroad:
YES | Company: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | 0 | 0
YES | Irrigation:
YES | Company: | 0 | 0 | 0 | 0 | Office #: | 0 | 15 | 0
YES | Name: | 0 | 0 | 0 | 0 | Title: | 0 | 16 | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | PreCon | 0
YES | Other:
YES | Company: | 0 | 0 | 0 | 0 | Office #: | 0 | For approval before placement | 0
YES | Name: | 0 | 0 | 0 | 0 | Title: | 0 | Before use of cement | 0
YES | Email: | 0 | 0 | 0 | 0 | Cell #: | 0 | Before use of fly ash | 0
YES | Other Stakeholders
YES | Organization: | 0
YES | Name: | 0 |  |  |  | Title: | 0
YES | Address: | 0 |  |  |  | Office #: | 0
YES | Email: | 0 |  |  |  | Cell #: | 0
YES | Organization: | 0
YES | Name: | 0 |  |  |  | Title: | 0
YES | Address: | 0 |  |  |  | Office #: | 0
YES | Email: | 0 |  |  |  | Cell #: | 0
YES | Organization: | 0
YES | Name: | 0 |  |  |  | Title: | 0
YES | Address: | 0 |  |  |  | Office #: | 0
YES | Email: | 0 |  |  |  | Cell #: | 0
NO | Organization: | [8 empty] | Phone Number - numbers only symbols not needed.
NO | Name: |  |  |  |  | Title:
NO | Address: |  |  |  |  | Office #
NO | Email: |  |  |  |  | Cell #:
NO | Organization:
NO | Name: |  |  |  |  | Title:
NO | Address: |  |  |  |  | Office #
NO | Email: |  |  |  |  | Cell #:
NO | Organization:
NO | Name: |  |  |  |  | Title:
NO | Address: |  |  |  |  | Office #
NO | Email: |  |  |  |  | Cell #:
NO | Organization:
NO | Name: |  |  |  |  | Title:
NO | Address: |  |  |  |  | Office # |  |  |  | Phone Number - numbers only symbols not needed.
NO | Email: |  |  |  |  | Cell #:
NO | Organization:
NO | Name: |  |  |  |  | Title:
NO | Address: |  |  |  |  | Office #
NO | Email: |  |  |  |  | Cell #:
NO | Organization:
NO | Name: |  |  |  |  | Title:
NO | Address: |  |  |  |  | Office #
NO | Email: |  |  |  |  | Cell #:
NO | Organization:
NO | Name: |  |  |  |  | Title:
NO | Address: |  |  |  |  | Office # |  |  |  | Phone Number - numbers only symbols not needed.
NO | Email: |  |  |  |  | Cell #:
NO | Organization:
NO | Name: |  |  |  |  | Title:
NO | Address: |  |  |  |  | Office #
NO | Email: |  |  |  |  | Cell #:
NO | Organization:
NO | Name: |  |  |  |  | Title:
NO | Address: |  |  |  |  | Office #
NO | Email: |  |  |  |  | Cell #:
NO | Organization:
NO | Name: |  |  |  |  | Title:
NO | Address: |  |  |  |  | Office #
NO | Email: |  |  |  |  | Cell #: