### August 26, 2004

# REVISION OF SECTION 109

RETAINAGE AND PARTIAL PAYMENTS

## NOTICE

This is a standard special provision that revises or modifies CDOT’s Standard Specifications for Road and Bridge Construction.  It has gone through a formal review and approval process and has been issued by CDOT’s Project Development Branch with formal instructions regarding its use on CDOT construction projects.  It is to be used as written without change.  Do not use modified versions of this special provision on CDOT construction projects, and do not use this special provision on CDOT projects in a manner other than that specified in the instructions unless such use is first approved by the Standards and Specifications Unit of the Project Development Branch.  The instructions for use on CDOT construction projects appear below.

Other agencies that use the Standard Specifications for Road and Bridge Construction to administer construction projects may use this special provision as appropriate and at their own risk.

Instructions for use on CDOT construction projects:

Use this standard special provision on all projects.

August 26, 2004

1

REVISION OF SECTION 109

RETAINAGE AND PARTIAL PAYMENTS

Sections 109 of the Standard Specifications are hereby revised for this project as follows:

Subsection 109.06 shall include the following:

- Prompt Payment. The Contractor shall pay subcontractors and suppliers for all work which has been satisfactorily completed within seven calendar days after receiving payment for that work from the Department. For the purpose of this section only, work shall be considered satisfactorily complete when the Department has made payment for the work.

The Contractor shall include in all subcontracts a provision that this requirement for prompt payment to subcontractors and suppliers must be included in all subcontracts at every tier.

The Contractor is responsible to ensure that all subcontractors and suppliers at every tier are promptly paid.

If the Contractor fails to comply with this provision the Engineer will not authorize further progress estimates until the required payments have been made and the Contractor agrees to make payments as specified.

- Retainage. The Contractor may withhold retainage of each progress estimate on work performed by subcontractors.  If during the prosecution of the project, a subcontractor satisfactorily completes all work described on CDOT Form No. 205, as amended by changes directed by the Engineer, the following procedure will apply:

- The subcontractor may make a written request to the Contractor for the release of the subcontractor’s retainage.

- Within ten working days of the request, the Contractor shall determine if all work described on Form 205 has been satisfactorily completed and shall inform the subcontractor in writing of the Contractor’s determination.

- If the Contractor determines that the subcontractor has not achieved satisfactory completion of all work described on Form 205, the Contractor shall provide the subcontractor with written notice, stating specifically why the subcontract work is not satisfactorily completed and what has to be done to achieve completion. A copy of this written notice shall be provided to the Engineer.

- If the Contractor determines that the subcontractor has achieved satisfactory completion of all work described on Form 205, the Contractor shall release the subcontractor’s retainage within 7 calendar days.

- In determining whether satisfactory completion has been achieved, the Contractor may require the subcontractor to provide documentation such as certifications and releases, showing that all laborers, lower-tiered subcontractors, suppliers of material and equipment, and others involved in the subcontractor’s work have been paid in full. The Contractor may also require any documentation from the subcontractor that is required by the subcontract or by the Contract between the Contractor and the Department or by law such as affidavits of wages paid, material acceptance certifications and releases from applicable governmental agencies to the extent that they relate to the subcontractor’s work.

- Within 14 calendar days after receiving the Contractor’s request, the Engineer will make inspection of all work described on Form 205. The Engineer will measure and furnish the final quantities to the Contractor of the items completed by the subcontractor. Agreement on these final quantities by the Contractor will not constitute the acceptance of the work described on Form 205 by the Engineer.

- If the subcontractor performs only a portion of an item of work, the Contractor shall release retainage in accordance with the procedures stated above and when the subcontractor has completed all of the work included in their subcontract, however, final measurement of quantities will not be made until the item of work and all of the work on the associated Form 205 has been completed.

August 26, 2004

2

##### REVISION OF SECTION 109

RETAINAGE AND PARTIAL PAYMENTS

- If additional quantities of a particular item of work are required at a later date after final measurement has been made, the Contractor shall perform this work in accordance with Contract requirements and at unit bid prices.

For this subsection only, satisfactory completion of all work described on CDOT Form No. 205 is when all tasks called for in the subcontract as amended by changes directed by the Engineer have been accomplished and documented as required by the Department.

The requirements stated above do not apply to retainage withheld by the Department from monies earned by the Contractor. The Department will continue to process the release of that retainage based upon the completion date of the project as defined in the Commencement and Completion of Work special provision.

The Contractor shall be solely responsible for all additional costs involved in paying retainage to the subcontractors prior to total project completion.

(g)	Good Cause Exception. If the Contractor has “good cause” to delay or withhold a subcontractor’s progress payment, the Contractor shall notify the Department and the subcontractor in writing within seven calendar days after receiving payment from the Department. The notification shall specify the amount being withheld and provide adequate justification for withholding the payment. The notice shall also clearly state what conditions the subcontractor must meet to receive payment. “Good cause” shall include but not be limited to the failure of the subcontractor to make timely submission of required paperwork

In subsection 109.09 delete the second paragraph and replace with the following:

All prior estimates and payments, except for those made in accordance with subsection 109.06(f) 6 will be subject to correction in the final estimate and payment.