## Sheet1
Project Risk Assessment Tool | [9 empty] | Catastrophic | Almost Certain
[10 empty] | Major | Likely
[10 empty] | Significant | Possible
Issue No. | Description of Issue | Issue Origination Date | Issue Owner | General Category | Likelihood | Consequence | CDOT Action | Contractor Action | Issue Closure Date | Minor | Unlikely
[10 empty] | Insignificant | Rare
1 | Safety - TMA's necessary in closed lanes for protection for workers and traveling public. 12' buffer lane when possible. UTC's in closures for visibility. Vehicle and equipment lights required for visibility. PPE for visibility and protection. | 2019-05-10 | Brannan | Traffic Control | Almost Certain | Major | 5/10/19 - Agrees to pay for TMA's and UTC's when necessary for safety | 5/10/19 - Agrees to follow safety measures outlined in project safety plan and follow MHT's | 2019-05-10
2 | 90 Day Schedule - Doable, but need to work together to achieve goal | 2019-05-10 | Brannan | Schedule | Possible | Major | CDOT needs to be aware of timeliness when approving submittals, resolving problems, responding to RFI's etc. | Brannan will follow schedule | 2016-06-03
3 | 7 Day pave back for bridge deck repairs - With moisture requirements for waterproofing membrane from manufacturer recommendations. 7 day pave back will be difficult if not impossible to achieve. | 2019-05-10 | Brannan/Lobato | Bridges | Almost Certain | Significant | CDOT will use discretion when enforcing pave back time | Brannan and Lobato will limit any delays from
4 | 4 Day pave back requirement for milled surface - Brannan built schedule based on this requirement. Better result if 5 days is allowed | 2019-05-10 | Brannan | Mill/Pave | Almost Certain | Significant | CDOT will evaluate milled surface to see if a 5 day pave back is acceptable
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47