## Workplan
Start Date | Task | Start | Finish | Predecessors | Work Complete | Resource
Curriculum
| Create Curriculum | 2017-03-01 | 2017-03-27 |  | 100% | Rachel Grafton, Lisa Cavalli, Gayle Rafferty, Jason Prince
| Review Curriculum | 2017-03-28 | 2017-04-17 |  | 100% | Beverly Wyatt, Mat Bjorge, Morgan Murphy, Rachel Grafton, Lisa Cavalli, Gayle Rafferty, Jason Prince
Project Plan
| Create Project Plan | 2017-04-03 | 2017-04-07 |  | 100% | Jason Prince
| Review Project Plan | 2017-04-05 | 2017-04-05 |  | 100% | Gayle Rafferty, Jason Prince
| Curriculum |  |  |  |  | Rachel Grafton, Lisa Cavalli, Gayle Rafferty, Jason Prince
| Approve Curriculum | 2017-03-28 | 2017-04-17 |  | 100% | Beverly Wyatt, Mat Bjorge, Morgan Murphy, Rachel Grafton, Lisa Cavalli, Gayle Rafferty, Jason Prince
Project Plan/Templates
| Approve Project Plan | 2017-04-05 | 2017-04-07 |  | 100% | Gayle Rafferty, Jason Prince
| Complete Template for eLearning Course | 2017-03-13 | 2017-03-17 |  | 100% | Jason Prince
| Complete Introduction /Conclusion | 2017-03-13 | 2017-03-17 |  | 100% | Jason Prince
| Complete Time Entry Overview | 2017-03-13 | 2017-03-17 |  | 100% | Jason Prince
| Review of Introduction/Conclusion Time Entry Overview and Template | 2017-04-03 | 2017-04-10 |  | 100% | Rachel Grafton, Lisa Cavalli
| Review of Introduction/Conclusion Time Entry Overview and Template | 2017-04-03 | 2017-04-10 |  |  | Gayle Rafferty, Jason Prince
2017-04-03 | Section Four Leave Time Entry (Intro to SAP time Entry)
Development
| Knowledge Transfer | 2017-03-28 | 2017-03-28 |  | 100% | Rachel Grafton, Lisa Cavalli, Jason Prince
| Draft Leave Time Entry Section | 2017-04-02 | 2017-04-10 |  | 50% | Jason Prince
| Review Complete Leave Time Entry Section | 2017-04-11 | 2017-04-14 |  | 100% | Rachel Grafton, Lisa Cavalli
| Create Enter and Release Leave uP Recording | 2017-04-11 | 2017-04-14 |  |  | Jason Prince
| Display Annual Use or Lose Report uP Recording | 2017-04-11 | 2017-04-14 |  |  | Jason Prince
| Display Leave Summary Report uP Recording | 2017-04-11 | 2017-04-14 |  |  | Jason Prince
| SME Review "Leave" Exercises (3) | 2017-04-18 | 2017-04-22 |  |  | Rachel Grafton, Lisa Cavalli
| Make Exercise Review edits | 2017-04-25 | 2017-04-25 |  |  | Jason Prince
| Functional review of leave exercise (3) section content | 2017-04-26 | 2017-04-29 |  |  | Gayle Rafferty
2017-04-10 | Section five Timesheet Verification and Section Two Time Entry Process (Intro to SAP time Entry)
Development
| Knowledge Transfer | 2017-04-11 | 2017-04-11 |  |  | Rachel Grafton, Lisa Cavalli, Jason Prince
| Draft Section Two and Five | 2017-04-10 | 2017-04-14 |  |  | Jason Prince
| Review Complete Leave Time Entry Section | 2017-04-17 | 2017-04-20 |  |  | Rachel Grafton, Lisa Cavalli
| Display Timesheet (variable time view) | 2017-04-17 | 2017-04-20 |  |  | Jason Prince
| Change Time Entry | 2017-04-17 | 2017-04-20 |  |  | Jason Prince
| Create Employee Time Entry Guide | 2017-04-17 | 2017-04-20 |  |  | Jason Prince
| Create Display ESS Time Entry Statement | 2017-04-17 | 2017-04-20 |  |  | Jason Prince
| SME Review Time Entry Exercises | 2017-04-24 | 2014-04-26 |  |  | Rachel Grafton, Lisa Cavalli
| Functional review of leave exercise (3) section content and Course Content | 2017-04-27 | 2017-05-01 |  |  | Gayle Rafferty
| Make Exercise Review edits | 2017-05-02 | 2017-05-03 |  |  | Jason Prince
2017-04-27 | Section Three Work Time Entry
Development
| Knowledge Transfer | 2017-04-18 | 2017-04-18 |  |  | Rachel Grafton, Lisa Cavalli, Jason Prince
| Draft Leave Time Entry Section | 2017-04-17 | 2017-04-20 |  |  | Jason Prince
| Review Complete Section 5 and Section 2 | 2017-04-17 | 2017-04-20 |  |  | Rachel Grafton, Lisa Cavalli
| Create ESS uP Recording | 2017-04-17 | 2017-04-20 |  |  | Jason Prince
| Create Display Annual Use or Lose Report | 2017-04-17 | 2017-04-20 |  |  | Jason Prince
| Create Employee Time Entry Guide | 2017-04-17 | 2017-04-20 |  |  | Jason Prince
| Create Display Leave Summary Report | 2017-04-17 | 2017-04-20 |  |  | Jason Prince
| SME Review Time Entry Exercises | 2017-05-01 | 2017-05-03 |  |  | Rachel Grafton, Lisa Cavalli
| Functional review of leave exercise (3) section content and Course Content | 2017-05-04 | 2017-05-10 |  |  | Gayle Rafferty
| Make Exercise Review edits | 2017-05-11 | 2017-05-12 |  |  | Jason Prince
2017-05-01 | Time Entry to Pay Course Finalization
| Record Scripts and finalize course | 2017-05-12 | 2017-05-16 |  |  | Jason Prince
| Publish course for final review | 2014-05-12 | 2017-05-12 |  |  | Jason Prince
| Final Review | 2017-05-12 | 2017-05-15 |  |  | Beverly Wyatt, Mat Bjorge, Gayle Rafferty
| Final Review Edit Changes | 2017-05-16 | 2017-05-19 |  |  | Jason Prince
| Publish and Upload course | 2017-05-19 | 2017-05-19 |  |  | Jason Prince, Gayle Rafferty
| Communicate eLearning is ready to take | 2017-06-15 |  |  |  | Gayle Rafferty
SAP Time Entry for Maintenance
2017-05-08 | Development of the SAP Time Entry for Maintenance S1-S2
Development
| Create Course Shell from Curricula | 2017-05-08 | 2017-05-10 |  |  | Jason Prince
| DATA BUILD Discussion (initial conversation what can we use from the previous) | 2017-05-09 | 2017-05-09 |  |  | ALL
| Knowledge Transfer for Review of Time Entry Section Overtime and Shift Premium Pay | 2017-05-09 | 2017-05-09 |  |  | Rachel Grafton, Lisa Cavalli, Jason Prince
| Create Ex 1 Enter and Release Working Time (Reactive/Routine) WI | 2017-05-08 | 2017-05-12 |  |  | Jason Prince
| Create Ex 2 Display Timesheet ZCAT3 WI | 2017-05-08 | 2017-05-12 |  |  | Jason Prince
| Create Review of Time Entry Course Lesson | 2017-05-08 | 2017-05-12 |  |  | Jason Prince
| Create Overtime and Shift Premium Lesson | 2017-05-08 | 2017-05-12 |  |  | Jason Prince
| SME Review of Review of Time Entry and Overtime and Shift Premium sections | 2017-05-15 | 2017-05-18 |  |  | Rachel Grafton, Lisa Cavalli
| Functional Review of Review of Time Entry and Overtime and Shift Premium sections | 2017-05-19 | 2017-05-23 |  |  | Gayle
2017-05-15 | Development of the SAP Time Entry for Maintenance S3
| Complete Changes to the Review of Time Entry and Overtime and Shift Premium sections | 2017-05-15 | 2017-05-19 |  |  | Jason Prince
| Knowledge Transfer Timesheet Collisions Caused by the Work Order | 2017-05-16 | 2017-05-16 |  |  | Rachel Grafton, Lisa Cavalli, Jason Prince
| Create Locate Work Order by Work Center IW49 WI | 2017-05-16 | 2017-05-19 |  |  | Jason Prince
| Display Timesheet CAT3 WI | 2017-05-16 | 2017-05-19 |  |  | Jason Prince
| Change Timesheet Variable View CAT2 WI | 2017-05-16 | 2017-05-19 |  |  | Jason Prince
| SME Review/Edit of Section 1 and 2 WI and Course Content | 2016-05-23 | 2016-05-25 |  |  | Rachel Grafton, Lisa Cavalli, Jason Prince
| SME Work Instruction for review | 2017-05-26 | 2017-06-01 |  |  | Rachel Grafton, Lisa Cavalli, Jason Prince
| Functional Review of Section and Work Instructions |  |  |  |  | Gayle Rafferty
2017-05-22 | Development of the SAP Time Entry for Maintenance S4
| Complete Changes to the Review of Time Entry and Overtime and Shift Premium sections | 2017-05-22 | 2017-05-26 |  |  | Jason Prince
DATA BUILD Discussion
| Knowledge Transfer Leave Entry and Alternate Holiday | 2017-05-23 | 2017-05-23 |  |  | Rachel Grafton, Lisa Cavalli, Jason Prince
| Create Display Leave Summary Report (ESS) WI | 2017-05-23 | 2017-05-26 |  |  | Jason Prince
| Enter and Release Leave Request CAT2 WI | 2017-05-23 | 2017-05-26 |  |  | Jason Prince
| SME Review/Edit of Section 3 WI and Course Content | 2017-05-29 | 2017-05-30 |  |  | Rachel Grafton, Lisa Cavalli, Jason Prince
| Functional Review of Course Materials | 2017-06-02 | 2017-06-05 |  |  | Gayle Rafferty
2017-05-29 | Earning Using Comp Time S5
| Complete Changes to the Review of Time Entry and Overtime and Shift Premium sections | 2017-05-29 | 2017-06-02 |  |  | Jason Prince
| Knowledge Transfer Leave Entry and Alternate Holiday | 2017-05-30 | 2017-05-30 |  |  | Rachel Grafton, Lisa Cavalli, Jason Prince
| Create Earning Comp Time Course Content | 2017-05-29 | 2017-06-02 |  |  | Jason Prince
| Create Change Comp Time to Annual Leave WI | 2017-05-30 | 2017-06-01 |  |  | Jason Prince
| SME Review/Edit of Section 4 WI and Course Content | 2017-05-29 | 2017-06-02 |  |  | Rachel Grafton, Lisa Cavalli, Jason Prince
| Functional Review edit changes made | 2017-06-01 | 2017-06-05 |  |  | Gayle Rafferty
2017-06-04 | Course Review and Finalization
| Complete s5 review edits | 2017-06-05 | 2017-06-05 |  |  | Jason Prince
| Finalize PPT | 2017-06-05 | 2017-06-05 |  |  | Jason Prince
| Send PPT for Review BPO Review | 2017-06-06 | 2017-06-09 |  |  | Beverly Wyatt, Mat Bjorge, Gayle Rafferty
| Final Review Edit Changes | 2017-06-12 | 2017-06-13 |  |  | Jason Prince
Logistics
| Prepare Materials for Class | 2017-06-14 |  |  |  | Gayle Rafferty
| Publish Materials to uPerform | 2017-06-14 |  |  |  | Gayle Rafferty
| Publish Materials to uPerform | 2017-06-14 |  |  |  | Gayle Rafferty
12/08 - 12/12
Delivery
| Deliver Training | 2017-07-19 | 2017-07-19 |  |  | TBD
Note: Jason is on vacation from July 7th to the 17th
Note: Contract renewal date is June 30th