## Revised Checklist
CDOT Project-level MS4 Construction Program Compliance Checklist
CDOT is working through an Administrative Order of Compliance on Consent (AOC) issued by the U.S. Environmental Protection Agency (EPA) to resolve non-compliant findings from the 2015 and 2019 EPA-led MS4 Permit compliance inspections. CDOT's Project-level MS4 Permit Compliance Tracking Form is part of this effort, informing each project's design and construction team of specific MS4 Permit compliance milestones that must be acheived at the project level for CDOT to be in compliance with its MS4 Permit. These compliance responsibilities are in addition to those assigned to Region Water Pollution Control Managers (RWPCMs) and other Region and Headquarters water quality staff through CDOT's MS4 Construction Program Manual.
CDOT's Colorado Discharge Permit System (CDPS) MS4 Permit requirements apply to all CDOT construction activities that result in a land disturbance of greater than or equal to one acre or that is less than one acre, but is part of a larger common plan of development or sale that would disturb, or has disturbed since March 2, 2001, one acre or more, unless excluded below or the disturbed areas have been finally stabilized. Covered construction activities include the land disturbing activity and all activities and materials associated with the construction project and located at or contiguous to the land disturbing activities. Covered construction activities typically hold a construction stormwater permit issued by CDPHE.
DRAFT January 18, 2022
Project Name: |  |  |  |  | SWMP Administrator:
Sub-account Number: |  |  |  |  | SWMP Preparer:
In MS4 or out? |  |  |  |  | SWMP Reviewer:
Region: |  |  |  |  | RWPCM(s):
CDOT Design Project Engineer(s)/Project Manager(s): |  |  |  |  | Design Engineer(s) Email:
CDOT Construction Project Engineer(s): |  |  |  |  | Construction Engineer(s) Email:
Question No. | Project in compliance? | Date Completed | Completed By | Compliance Milestone | Typical Project Phase | Requirement | Source of Requirement | Required Documentation | Location of Supporting Documents
1 | Yes |  | Name (Title) | The Project completed CDOT's Permanent Water Quality Evaluation and Tracking (PET) Form. | Design Phase | The PET Form must be preliminarily completed at FIR to determine whether the project requires an Onsite Permanent Water Quality Control Measure (PWQ CM) per a PWQ Onsite Required Trigger and if so whether Mitigation Pool Funding will be used. | MS4 Permit, Part I.E.2. | PET Form, Form 128 (Section C) | Project files
2 | Yes |  | Name (Title) | A CDOT-certified SWMP Preparer designed the Project SWMP. If applicable - this was inclucded as a technical requirement and deliverable in the request for proposal. | Design Phase | The project's SWMP must/shall be designed by a SWMP Preparer with an active CDOT SWMP Certification. The SWMP Preparer may be CDOT employed or Contractor employed. | MS4 Construction Program Manual | SWMP Preparer's CDOT certification number | Project SWMP
3 | Yes |  | Name (Title) | CDOT reviewed and accepted the SWMP prior to construction and the Project files contain confirmation of that review and acceptance on Form 128 or alternate SWMP acceptance document (depending on Region - consult with RWPCM or Environmental Manager). | Design Phase | Recordkeeping: CDOT must maintain a copy of the final SWMP reviewed to meet the initial SWMP review requirement, and confirmation of the permittee’s review and acceptance. A CDOT SWMP Reviewer (with a CDOT SWMP Certification), who is a full-time CDOT employee from CDOTs environmental team, must peer review the SWMP for each project per the requirements of Part 1.E.1.a.iv(B) of the MS4 Permit. A SWMP Reviewer may not review a SWMP they prepared. | MS4 Permit, Part I.E.1.b.iv. MS4 Construction Program Manual | Form 128 or alternate SWMP acceptance document | Project files
| Yes |  | Name (Title) | A copy of the final SWMP reviewed to meet the initial SWMP review requirement is saved in the Project files. |  |  |  | Recordkeeping: CDOT must maintain a copy of the final SWMP reviewed to meet the initial SWMP review requirement, and confirmation of the permittee’s review and acceptance. | Project files
4 | N/A |  | Name (Title) | The Project is located within or drains to the Cherry Creek Reservoir Drainage Basin and the SWMP complies with construction BMP (control measure) requirements listed in CDPHE-WQCD Regulation No. 72 - Cherry Creek Reservoir Control Regulation (5 CCR 1002-72). (select "N/A" if the Project is outside the Cherry Creek Reservoir Drainage Basin) | Design Phase | Cherry Creek Reservoir Drainage Basin Discharges: All MS4 Permit control measure requirements (Part I.B.) must be met for those parts of the MS4 that drain into the Cherry Creek Reservoir drainage basin. In addition, the permittee must also meet the requirements in Cherry Creek Reservoir Control Regulation (5 CCR 1002-72). | MS4 Permit, Part I.E.1.a.viii. MS4 Permit, Part I.E.1.b.viii CDPHE-WQCD Regulation No. 72 | Cherry Creek Reservoir Drainage Basin Discharges: The applicable specifications, contracts, standards; operating procedures, and other documents used to meet the permit requirements. | Project files
Question No. | Project in compliance? | Date Completed | Completed By | Compliance Milestone | Typical Project Phase | Requirement | Source of Requirement | Required Documentation | Location of Supporting Documents
5 | Yes |  | Name (Title) | The Project obtained water quality agreements with neighboring Local Agencies, prior to construction (if a project overlaps two or more MS4 permit areas, the project must have agreements in place with the overlapping MS4 that define which requirements will be followed, who will oversee/inspect, etc.). (select "N/A" if Local Agency agreements are not required) | Design Phase | For Covered Construction Activities that Overlap Permit Areas of more than One MS4 Permittee (co-regulating MS4 permittee), when a written agreement is in place with a co-regulating MS4 permittee: Control measure, SWMP, and inspection requirements may be imposed on the operator in accordance with the requirements of a co-regulating MS4 permittee pursuant to the written agreement. | MS4 Permit, Part I.E.1.a.ix. MS4 Permit, Part I.E.1.b.ix. | Recordkeeping: For Covered Construction Activities that Overlap Permit Areas of more than One MS4 Permittee: Copies of any written agreements between co-regulating MS4 permittees. | Project SWMP
6 | Yes |  | Name (Title) | The Project's Contract includes only the AD-date version of CDOT's Standard Water Quality Specifications, without modification. (if yes, go to question 7) | Design Phase | The Project shall adhere to CDOT’s Water Quality Specifications without modification, excepting payment and measurement sections, without further review and acceptance. CDOT’s Water Quality Specifications are Standard Specifications for Road and Bridge Construction (current version), subsection 107.25 and Sections 208, 213 and 216; M&S Plans M-208-1 and M-216-1. | CDOT MS4 Construction Program Manual Standard Specifications for Road and Bridge Construction (current version in contract), subsection 107.25 and Sections 208, 213 and 216; M&S Plans M-208-1 and M-216-1. | Project contract | Project files
| N/A |  | Name (Title) | If the Project's Contract includes one or more project special provisions to the Water Quality Specifications, the Project consulted with the Region Water Pollution Control Manager before and during development of the project special provision(s). |  |  |  | The project files must contain the appropriate documentation or CMO justifying the use of previous or modified versions of either the specifications or contract language. | Project files
7 | Yes |  | Name (Title) | The environmental preconstruction conference discussed CDOT's expectations regarding SWMP implementation and maintenance, CDOT MS4 inspections, and the MS4 Construction Program's enforcement mechanism. | Construction Phase | Prior to Work commencing, an environmental pre-construction conference shall be held with one of CDOT’s RWPCMs. | CDOT MS4 Construction Program subsection 208.03 | Conference agenda with a certification of understanding signed by all attendees. | Project files Project SWMP
8 | N/A |  | Name (Title) | The RWPCM and Project Engineer/Project Manager are included in all stormwater related communications between the Contractor and CDPHE, EPA, or other regulatory agencies. | All Phases | The Contractor shall include CDOT in all communication with regulatory agencies. | CDOT MS4 Construction Program |  | Project files Project SWMP
9 | N/A |  | Name (Title) | CDOT provided written approval before any changes to the Contractor's SWMP Adminstrator or Erosion Control Inspectors (ECIs). | Active and Post-active Construction | Changing the person assigned as the SWMP administrator and/or the ECI after the project starts requires written Approval by CDOT. | CDOT MS4 Construction Program | Form 105 documenting CDOT approval of changes to to the Project SWMP Admin and ECI | Project SWMP
Question No. | Project in compliance? | Date Completed | Completed By | Compliance Milestone | Typical Project Phase | Requirement | Source of Requirement | Required Documentation | Location of Supporting Documents
10 | N/A |  | Name (Title) | The RWPCM and SWMP Reviewer are consulted on all major SWMP modifications. (The RWPCM reviews all minor modifications during all routine MS4 inspections) | Active and Post-active Construction | The permittee [CDOT] must develop and implement procedures to address modifications to SWMPs including how minor and major modifications are defined and reviewed. A CDOT SWMP Reviewer (with a CDOT SWMP Certification), who is a full-time CDOT employee from CDOTs environmental team, must peer review the SWMP for each project per the requirements of Part 1.E.1.a.iv(B) of the MS4 Permit. A SWMP Reviewer may not review a SWMP they prepared. | MS4 Permit, Part I.E.1.a.iv.A. CDPHE-WQCD defines major SWMP modifications as “[c]hanges to the original site plan that remove or add additional area to the project, modify the final hydrology or drainage of the final design, replace approved site plans, or otherwise expand or contract the scope of the original project shall require the submission of plans to the permittee for review and approval.” CDOT adds the additional condition that a major SWMP modification is one that occurs when a change to project conditions triggers a Change Order, as defined in Section 100 of the CDOT Construction Manual. | Form 105 and Change Order Modification (CMO) documenting acceptance of Major SWMP Modification | Project SWMP
11 | N/A |  | Name (Title) | CDOT has a contingency plan if the site does not achieve final stabilization from permanent stabilization (the process for this varies by Region, consult with the RWPCM or Environmental Manager for the project). | Design/Post-active Construction | Permanent stabilization is defined as the covering of disturbed areas with topsoil, seeding, mulching with tackifier, soil retention coverings, and such non-erodible methods as riprap, road shouldering, etc., or a combination thereof as required by the Contract. (subsection 208.04.e.4) “Final stabilization” is the condition reached when all ground surface disturbing activities at the site have been completed, and for all areas of ground surface disturbing activities a uniform vegetative cover has been established with an individual plant density of at least 70 percent of pre-disturbance levels, or equivalent permanent, physical erosion reduction methods have been employed. | MS4 Permit | SWMP, contract documents pertaining to Permanent Stabilization | Project files
12 | N/A |  | Name (Title) | The RWPCM was present for the final Project walkthrough. | Post-active Construction | Prior to Final Acceptance of the Project, the Contractor will notify CDOT’s RWPCM that the project is ready for a final walkthrough inspection. The RWPCM will be notified at least 14 calendar days prior to the anticipated inspection. Any items identified for maintenance, replacement, or removal shall be done immediately or non-compliance with associated penalties per subsection 208.09 may be incurred by the Contractor. | CDOT Specifications | RWPCM report from the final Project walkthrough | RWPCM's project inspection reports
13 | N/A |  | Name (Title) | All maintenance, replacement, or removal items identified during the final walkthrough were addressed by the Contractor prior to Final Acceptance. | Post-active Construction | Prior to Final Acceptance of the Project, the Contractor will notify CDOT’s RWPCM that the project is ready for a final walkthrough inspection. The RWPCM will be notified at least 14 calendar days prior to the anticipated inspection. Any items identified for maintenance, replacement, or removal shall be done immediately or non-compliance with associated penalties per subsection 208.09 may be incurred by the Contractor. | CDOT Specifications | Contractor's response to findings from the final Project walkthrough | Project files Project SWMP
14 | N/A |  | Name (Title) | The Project worked with the RWPCM to terminate the CDPS-SCP when the Project achieved Final Stabilization in accordance with the SWMP. | Post-active Construction | CDPS-SCP coverage for a site that has been finally stabilized in accordance with the SWMP may be terminated. | CDPHE Construction Stormwater Permitting FAQ (https://oitco.hylandcloud.com/POP/DocPop/DocPop.aspx?docid=3154537) | CDPS-SCP Notice of Termination (NOT) | Project files Project SWMP
DRAFT
DRAFT
DRAFT